## Project Settings
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Javier Mesa
Start Date | abr 23, 2017 04:02:13 PM
Completion Date | abr 28, 2017 09:18:50 PM | Completed: *
Keywords
Language | Java
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:50 PM el 29/04/2017

## Overall Metrics
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 24.2 | 23.4 | 26.1
Planned Time | 0.19028 |  | 1899-12-31 08:11
Actual Tiempo |  | 0.20625 | 1899-12-31 10:25
CPI (Cost-Performance Index) |  |  | 0.94
% Reuse | 66.3% | 65.5% | 32.9%
% New Reusable | 0% | 0% | 0%
Test Defects/KLOC or equivalent | 0 | 0 | 0
Total Defects/KLOC or equivalent | 20.4 | 0 | 17.8
Yield % | 75% | #DIV/0! | 75%
Code Review Rate | 411 | 211 | 394
% Appraisal COQ | 10.2% | 22.9% | 12%
% Failure COQ | 12.4% | 7.41% | 11.7%
COQ A/F Ratio | 0.82 | 3.09 | 1.02
PQI | 0.11 | 0.65 | 0.17
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:46 PM el 29/04/2017

## Program Size
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Program Size
| Plan | Actual | A la Fecha
Base (B) | 375 | 375 | 1120
Deleted (D) | 330 | 327 | 924
Modified (M) | 0 | 0 | 78
Added (A) | 110 | 116 | 821
Reused (R) | 306 | 311 | 499
Added and Modified (A+M) | 110 | 116 | 899
Total Size (T) | 461 | 475 | 1516
Total New Reusable | 0 | 0 | 0
Estimated Proxy Size (E) | 116 | 116 | 789
Upper Prediction Interval (70%) | 117
Lower Prediction Interval (70%) | 103
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:47 PM el 29/04/2017

## Time In Phase
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.047222 | 0.045833 | 0.35139 | 24.5%
DiseÃ±o | 0.031944 | 0.034722 | 0.23889 | 16.7%
RevisiÃ³n de DiseÃ±o | 0.0083333 | 0.024306 | 0.077083 | 5.38%
CodificaciÃ³n | 0.056944 | 0.049306 | 0.41597 | 29%
RevisiÃ³n de CodificaciÃ³n | 0.011111 | 0.022917 | 0.095139 | 6.63%
CompilaciÃ³n | 0.013194 | 0.00625 | 0.090972 | 6.34%
Pruebas | 0.010417 | 0.0090278 | 0.077083 | 5.38%
Postmortem | 0.011111 | 0.013889 | 0.0875 | 6.1%
Total | 0.19028 | 0.20625 | 1899-12-31 10:25
Total Time UPI (70%) | 0.225
Total Time LPI (70%) | 0.15486
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:47 PM el 29/04/2017

## Defects Injected
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0.14 | 0 | 1 | 6.25%
DiseÃ±o | 1.13 | 0 | 8 | 50%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.99 | 0 | 7 | 43.8%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 2.25 | 0 | 16
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:53 PM el 29/04/2017

## Defects Removed
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.42 | 0 | 3 | 18.8%
CodificaciÃ³n | 0.99 | 0 | 7 | 43.8%
RevisiÃ³n de CodificaciÃ³n | 0.28 | 0 | 2 | 12.5%
CompilaciÃ³n | 0.56 | 0 | 4 | 25%
Pruebas | 0 | 0 | 0 | 0%
Total | 2.25 | 0 | 16
After Development | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:53 PM el 29/04/2017

## Defect Removal Efficiency
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 2.15 | 0 | 1.62
Defects/Hour - Code Review | 1.05 | 0 | 0.88
Defects/Hour - Compile | 1.79 | 0 | 1.83
Defects/Hour - Test | 0 | 0 | 0
DRL (DLDR/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Code Review/UT) | #VALUE! | #DIV/0! | #DIV/0!
DRL (Compile/UT) | #VALUE! | #DIV/0! | #DIV/0!
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 09:54 PM el 29/04/2017